## Agile Sheet
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a user, I want a menu-driven interface so that I can navigate banking operations easily. | M | NA | Pranav S. Kedar | Completed
Sprint 1 | Sprint 1 | US-02 | As a user, I want to create a bank account with an initial balance so that I can start transactions. | M | US-01 | Pranav S. Kedar | Completed
Sprint 1 | Sprint 1 | US-03 | As a user, I want the system to accept my inputs correctly so that I can perform banking tasks without errors. | M | US-01 | Pranav S. Kedar | Completed
Sprint 2 | Sprint 2 | US-04 | As a user, I want to deposit money into my account so that my balance increases. | M | US-02 | Pranav S. Kedar | Completed
Sprint 2 | Sprint 2 | US-05 | As a user, I want to withdraw money with proper validation so that I cannot exceed my balance. | M | US-04 | Pranav S. Kedar | Completed
Sprint 2 | Sprint 2 | US-06 | As a user, I want to check my account balance so that I know my current funds. | M | US-02 | Pranav S. Kedar | Completed
Sprint 3 | Sprint 3 | US-07 | As a user, I want input validation so that invalid choices and amounts are not accepted. | S | US-05 | Pranav S. Kedar | Completed
Sprint 3 | Sprint 3 | US-08 | As a user, I want clear messages and smooth program flow so that the system is easy to use. | C | US-01 | Pranav S. Kedar | Completed
Sprint 3 | Sprint 3 | US-09 | As a developer, I want to test and integrate all modules so that the banking system works correctly as a whole. | M | US-08 | Pranav S. Kedar | Completed
Sprint 3 | Sprint 3 | US-10 | As a user, I want authentication before accessing account details so that my data remains secure. | M | US-02 | Pranav S. Kedar | Completed
Sprint 3 | Sprint 3 | US-11 | As a new user, I want to register with my credentials so that I can create an authenticated account. | M | US-10 | Pranav S. Kedar | Completed
Sprint 3 | Sprint 3 | US-12 | As a registered user, I want secure login and session control so that unauthorized access is prevented. | S | US-11 | Pranav S. Kedar | Completed